## Sheet1
ID | Story | Priority | Estimate | Status
1 | How to read the image in | 1 | 1 | done?
2 | How to divide a given image into 4 quadrants | 1 | 2
3 | Determine when an image is a leaf | 1 | 2
4 | Determine when an image is NOT a leaf | 1 | 1
5 | Determine the quadrant of each image | 1 | 1
6 | Determine the four children of a node | 1 | 1
7 | How to draw a black node on the screen | 1 | 1 | done?
8 | How to draw a white node | 1 | 1 | done?
9 | How to draw a grey node | 1 | 1 | done?
10 | How to draw an arrow from one node to next | 1 | 1 | done?
11 | How to determine the position of the point (node) | 2 | 1
12 | How to move the points around on the screen | 2 | 2
13 | How to move one end of an arrow (with node) to a different place | 2 | 2
14 | How to move the whole arrow | 3 | 2
15 | How to move the entire quadtree | 3 | 2
16 | How do I rescale the quadtree | 3 | 2
17 | Add control panel | 3 | 2 | done?
18 | Divide screen (other than control panel) into two halves: image & quadtree | 3 | 5 | done?
19 | Display image on left side | 3 | 2 | done?
20 | Display quadtree | 1 | 3
21 | Create "load image" button | 2 | 1 | in progress
22 | Create "display image" button | 2 | 1 | in progress
23 | "Save image" button | 4 | 1 | in progress
24 | "Close the image" | 4 | 1 | in progress
25 | "Load quadtree" button | 2 | 1 | in progress
26 | "Display quadtree" button | 1 | 1 | in progress
27 | "Save quadtree" button | 3 | 1 | in progress
28 | "Close quadtree" button | 3 | 1 | in progress
29 | Quadtree to image | 2 | 15
30 | Image to quadtree | 2 | 15
31 | "Automate" button | 2 | 4
32 | "Manual" button | 2 | 4
81
INTERNAL
0 | Visual Studio/C# training spike | 0 | 8
n+1 | Code clean up | 0 | 8
16